## Slide 1: Case Study: Real Lessons for Technical Writing Projects… or… Why a TWENTY hour project took ONE HUNDRED AND TWENTY HOURS!

## Slide 2: Case Study Details
Hi-tech company in Israel
Project: Engineering document (“100 or so pages” “mostly editing” “we’ll give you all the information”)
Estimate…what estimate?
  20 hours
  Firm deadline…no buffer

## Slide 3: First Meeting – Client Description
Met lead engineer and product manager
Shown a 100 page requirements document
Told to produce 100 pages of text
Told it was “mostly editing”
Lead engineer: “20 hours” for him to do it
Deadline
  6 days later (10 hour days? 60 hours?)
  Leaving 7 days for printing and compiling
  3 days for overnight/2 day deliver
Company authorized 40 hours

## Slide 4: First Meeting – Our Thoughts
  Too much information was missing
  Unclear what they wanted beyond editing
  Lead engineer didn’t really understand documentation
  Pressured to begin the work w/o outline/estimate
  6 days later (10 hour days? 60 hours maximum)

## Slide 5: What Wasn’t Done at the First Meeting
Outline of the project
Clear understanding of WHO would assist us
Wrong file delivered to us
International agency requirements were poorly written…then interpreted by company’s engineers (incorrectly)
Several different engineers were given pieces of the requirements document – no lead on their side assigned

## Slide 6: Lesson One
Plan ahead!
  Define –
    WHO are the contact people
    WHAT responsibility each person has
    WHAT are the deliverables (format, contents)
    WHEN must they deliver (deadlines)
    WHAT will YOU be responsible for

## Slide 7: Don’t underestimate the important of estimating
Normal project requirements: outline and estimate
This project: no outline (mistake?)

## Slide 8: Making an Estimate
Have an SME SHOW you the product
Take your time (count the windows, menus, questions, and calculate length and time for each)
Don’t forget the extras (TOC, index, layout)
Include a buffer – always unknown factors, additional review cycles, unrevealed features
Be prepared to walk away

## Slide 10: Outline Should Include:
List of sections
Reference to existing materials
List of contact people (related to sections)
Amount of pages (topics)
How long it should take (hours/days)
Minimal in content

## Slide 11: Why Do You Need an Outline?
So everyone agrees on content
Standing record
Measure of what needs to be done/what was done/ what remains
Bottom line: good chance of success with; good chance of failure without

## Slide 12: Assess the Materials On Hand
Difference between major and minor…what content exists
Can’t calculate true deadlines
In our project:
  Resources kept “popping up”
  Version control
  Source documents missing

## Slide 13: Determine the Flow of Responsibilities
To meet the time requirements – 3 writers
Single points of contact (writer/engineer)
External experts?
Print and edit?

## Slide 14: Coping with Insanity
Acceptance – things happen
Make the client understand
Evaluate progress against remaining tasks
Red lines and black lines and red lines
Shift to new realities

## Slide 15: Keep a Sense…
Of Humor: TW deadline 12 noon Friday; engineer’s deadline Saturday midnight? Um…no.
Of Quality: yes, we need to proof it, really.
Of Deadlines: real ones.
  No, no 7 days to print (overnight);
  No 3 days delivery. 12 hour flight; 1 hour taxi

## Slide 16: Summary

## Slide 17: Lessons for Tomorrow
Consider investing more time going through ALL requirements
Line up all the materials IN ADVANCE
Original job: Preparing materials and assembling final document
  Focus was on preparing
  Assembling was huge, unanticipated element not defined

## Slide 18: Lessons for Tomorrow
Initial meeting should have included
  In-depth analysis of ALL requirements
  Creating an outline (rather than their Excel) – with responsible parties
Don’t hesitate to bring in more resources if needed
  Company OK came too late to be practical
  Client was initially happy w/ 2 writers

## Slide 19: Lessons for Tomorrow
Consider interviewing the engineers
  Client wanted engineers to write – not good…
  Engineer in Ireland? Scan and print?

## Slide 20: Lessons for Client
Time the entrance
Version control
Check info BEFORE giving to tech writers
  Are you Ltd. LLC, Inc., Corp?
Teamwork
Estimations – trust writers who regularly create documentation

## Slide 21: So, WHY did it take 120 hours?
10 hours was lost working on the customer’s file…till they told us it was the wrong file (times 2)
3 hours with scan/print/telephone corrections
Company told us to do A, then B, then C (change company name to Name Inc. – No, Ltd. no…Corp.) – other changes (7 hours)
Total wasted: 20 hours

## Slide 22: So, WHY did it take 120 hours?
Not factored into their “20 hours”
  Compliance requirements – review and implementation – 10 hours (read, check, read, check, fix, check, read)
  Assembly part took approximately 20 hours (not factored in)
  Layout issues were huge (different writers, different formatting) – 5 hours
  Total: 20 + 35 = 55

## Slide 23: So, WHY did it take 120 hours?
120 page document…was 180 pages long
5-6 day project took 12 days (long hours)
16-22 hour days?

## Slide 24: Final Comments
Project was a success
Few other companies followed guidelines, while our client did
Document was delivered on time (by plane)
Document was printed in house

## Slide 25: And final lesson – share your knowledge